## Project Descriptions
IP | Project | Description
628 | Establishment Licensing and Inspections | There are a number of different post-market programs at Health Canada that authorize applicants to conduct regulated activities, against regulated products, at specific locations. These include: • Medical Device Establishment Licensing (RORB) • Natural Health Product Site Licensing (HPFB) • Controlled Substances Dealer Licensing (HECSB) • Drug Establishment Licensing (RORB) There are two active IP projects (CSPS and e-CES) that include this functionality. It is also expected that the Cannabis legalization program will require this functionality. Most programs in this space are using systems with growing aging IT risks, or are still having to use paper and spreadsheet based processes. Intended direction is to identify and acquire a highly configurable COTS product that is targeted at the regulatory licensing space. This solution will be available to all programs as their primary option for this capability. Functionality that is within scope of solution is: • application intake, review, and triage • inspections that support licence decisions • risk assessment • decision workflow • license/permit generation and notification • calculation & collection of license fees (cost recovery)
A01 | RORB Data Analytics & Business Solutions | Support branch with excellence in data analytics; build the data literacy within ROEB together with community to establish a core foundation to sound data analytics principles and practices; and accelerate ROEB applied data driven projects to improve our experience with data driven decision making.
A03 | Enabling Compliance and Enforcement Program Delivery | To enable RORB to better support enhanced efficiency and effectiveness in Compliance and Enforcement program delivery investments will be made in learning management, inspection scheduling, assisted human reproduction, fleet, client service tools, and Infrastructure and Software as a Service.
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | There are 28 RORB IT solutions that are considered Aging IT. Systems will be addressed by priority and grouped with projects of similar priority. There are 28 RORB IT solutions that are considered aging IT. RORB will conduct a review of aging IT systems and produce a plan to remediate through tolerating, migrating, innovating, or eliminating these systems. High priority systems under aging IT include: Inspection Reporting System, Incident System, Export Certificate Database, and the Laboratory Information Management System.
810 | Drug and Health Product Inspections Database | As part of the regulatory transparency priority, seven different programs make use of the online Inspection Database to post their inspection reports to the Healthy Canadians website, where the public has access to them. Due to the challenges experienced when making changes to DHPID, the system is being rewritten in order to make future enhancements easier to manage and less resource intensive. This will also better prepare us for when inspection data will come from IP-628 solution.
A06 | Modernizing the RORB Employee eToolkit | This project focuses on providing off-the-shelf hardware and software solutions to employees working in the RORB program to modernize the workforce and enable a seamless transition from office to the field. It addresses challenges in the technology currently made available to RORB employees and proposes alternative solutions that would allow them to do their jobs more efficiently.
701 | Border IM/IT Modernization | Invest in a modern IM/IT system for the Health Products Border Program to bring their data collection and management processes onto a single mobile platform, with the following key features: • Workload management • Process standardization • Data quality and structure • Enterprise collaboration • Reporting This IT system will replace two Lotus Notes databases and numerous Excel spreadsheets being used by the health products border program. This initiative is closely linked with Business Analysis/Risk Intelligence initiatives outlined above.
704 | Quality Management System | System for Quality Management (ISO 9001:2000): is part of a suite of databases designed specifically to meet the requirements of ISO 9001:2000, the QSI System for Quality Management helps an organization reap the benefits of ISO certification, including improved customer satisfaction and reduced costs. QSi, the software suite used to manage a Quality Management System (QMS) is currently unsupported and is housed on an Aging IT Platform (Lotus Notes). The software suite is inherently unstable and contains many bugs. The RORB programs using QSi (Labs, HPCD, MDCCD) are concerned of a system collapse and how it could potentially impact current Accreditation and Mutual Recognition Agreements in place.
705 | DAS Modernization | Modernization of the DAS Labs business proecess and introduction of an end-to-end IT solution for the submission, triage, assessment, and issuance of the DAS Certificate of Analysis.
Cyclops | Cyclops | The project is proposing to create a new process enabled by a digital-tool (smartphone camera / wearable device) to virtualize optically represented text on the label, query the data via existing databases, identify and highlight instances of non-compliances, and visually depict the issue by overlaying the information back on to the camera/device feed. This will allow Inspectors to review the labels on-site, without the need to collect samples and invest more time into the inspection. As a small scale proof of concept, a solution can be developed using the minimal viable product model for Natural Health Products and targeted for Inspectors in the Health Product Compliance and the Border Integrity Unit for testing.
Hummingbird | Hummingbird | Using Unmanned Aerial Systems (UAS) create a new outdoor inspection system to positively impact the operational activities of inspectors. Initial focus is to achieve benefit to inspectors within Cannabis, Controlled Substances (Opium Poppy), and Pesticide programs. The major goals of the project include: • Identify, address and fill the gaps within the current limitations in the field. • Provide inspectors with more accurate and modernized tools. • Ensure better safety for inspectors. • Utilize the vast data collected through Unmanned Aerial Vehicles (UAV) to aid inspectors in real time inspections as well as help Health Canada better understand non-compliance patterns and loopholes.
Cipher | Cipher | This project will serve as a vehicle for Health Canada to explore and experiment with text mining, natural language processing, machine learning and artificial intelligence to mine inspection reports for insight and actionable information that would support prospective and predictive analysis.
Kelpie | Kelpie | This project will initially explore whether it’s possible to use artificial intelligence to monitor social media and identify “posts” promoting vaping products that could be appealing to youth. While the initial focus is to acheive benefit for the Tobacco and Vaping C&E program, what we learn will also benefit other HC programs.
IP809 | PCP IT Modernization | This project aims to bring together all pesticide compliance and enforcement information into one IT system and provide a platform for managing workload, standardizing processes and reporting on performance.
IP811 | CSP IT Modernization | This project aims to proceed with the development of a new IT system that provides modernized & interconnected tools for the Controlled Substance Program(CSP) in support of the delivery of its mandate of controlled substances regulatory compliance and enforcement oversight across Canada.

## Schedule
IP | Project | Directorate | Major.Milestone | Major.Milestone.Standard | Approved_finish_date | Actual_date | Schedule.Health | Schedule.Health.Standard
A03 | Enabling Compliance and Enforcement | TBI | Pilot LMS: Cannabis | Pilot LMS: Cannabis | 2018-07-01 | 2018-07-01 | Completed on time | completed
A03 | Enabling Compliance and Enforcement | TBI | Pilot JIRA: First 3 instances (DEL, Border, AMS) | Pilot JIRA: First 3 instances | 2018-09-01 | 2019-01-01 | Completed within 3 months of projeccted baseline date. | completed | `
A03 | Enabling Compliance and Enforcement | TBI | Pre-build activities - LMS: Tobacco & Vaping | T&V Prebuild | 2018-11-01 | 2018-11-16 | Completed on time | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #1) - LMS: Tobacco & Vaping | T&V Build Dev #1 | 2018-11-16 | 2018-12-15 | Completed within 1 month of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Pilot LMS: Tobacco and Vaping | Pilot LMS: T&V | 2019-02-01 | 2019-12-01 | Completed within 2 months of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Pre-build activities - LMS: Health Product Inspection and Licensing | Health Product Prebuild | 2018-12-01 | 2019-02-15 | Completed within 3 months of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #1) - LMS: Health Product Inspection and Licensing | Health Product Build Dev #1 | 2019-02-15 | 2019-03-10 | Completed within 1 month of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #2) - LMS: Health Product Inspection and Licensing | Health Product Build Dev #2 | 2019-05-10 | 2019-07-01 | Completed within 2 month of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Jira to Production server | Jira to Production server | 2020-01-10 |  | Forecasted completion within 6 months of baseline date. | forecasted completion within 3-6 months of baseline date
A03 | Enabling Compliance and Enforcement | TBI | Pre-build activities - JIRA: HPCD (QMS Document Tracking) | HPCD Prebuild | 2019-03-11 | 2019-04-08 | Completed within 1 month of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Jira Outlook Integration | Jira Outlook Integration | 2019-05-15 | 2019-09-15 | Completed within 6 months of projected baseline date | completed
A03 | Enabling Compliance and Enforcement | TBI | Pre-build activities - LMS: Controlled Substances | Controlled Substances Prebuild | 2019-10-15 | 2019-10-15 | Completed on time | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #1) - LMS: Controlled Substances | Controlled Substances Build Dev #1 | 2020-02-01 | 2020-02-01 | Completed on time | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #2) - LMS: Controlled Substances | Controlled Substances Build Dev #2 | 2020-05-01 | 2020-05-01 | Completed on time | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #1) - LMS: HP Labs | HP Labs Build Dev #1 | 2019-11-01 | 2019-12-20 | Completed within 1 month of projected baseline date. | completed
A03 | Enabling Compliance and Enforcement | TBI | Build activities (Dev #2) - LMS: HP Labs | HP Labs Build Dev #2 | 2019-12-20 | 2019-12-20 | Completed on time | completed
A03 | Enabling Compliance and Enforcement | TBI | Jira build phase #1 - TCVEP Inspection Scheduling System | Jira build phase #1 - TCVEP Inspection Scheduling System | 2020-09-01 | 2020-09-01 | Completed on time | Forecasted completion on time
A03 | Enabling Compliance and Enforcement | TBI | Jira build phase #1 - BPCP Issues Tracker | Jira build phase #1 - BPCP Issues Tracker | 2020-10-01 | 2020-10-01 | Completed on time | Forecasted completion on time
628 | Establishment Licensing and Inspections | CSB | Procurement Management Plan | Procurement Management Plan | 2019-01-31 | 2019-06-18 | Completed within 6 month of projected baseline date. | completed
628 | Establishment Licensing and Inspections | CSB | Privacy Impact Assessment completed | Privacy Impact Assessment completed | 2019-06-30 | 2019-03-01 | Completed ahead of time | completed
628 | Establishment Licensing and Inspections | CSB | CTLS Fit Gap analysis | CTLS Fit Gap analysis | 2019-05-31 | 2019-06-14 | Completed within 1 month of projected baseline date. | completed
628 | Establishment Licensing and Inspections | CSB | LEAN analysis completed | LEAN analysis completed | 2019-05-31 | 2019-06-10 | Completed within 1 month of projected baseline date. | completed
628 | Establishment Licensing and Inspections | CSB | Statement of Work completed | Statement of Work completed | 2019-07-15 | 2020-01-14 | Completed within 6 month of projected baseline date. | completed
628 | Establishment Licensing and Inspections | CSB | Business transformation plan | Business transformation plan | 2019-11-30 | 2020-12-11 | Completed within 1 month of projected baseline date. | completed
628 | Establishment Licensing and Inspections | CSB | PSPC Approvals | PSPC Approvals | 2020-03-13 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
628 | Establishment Licensing and Inspections | CSB | RFP Posted | RFP Posted | 2020-04-09 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
628 | Establishment Licensing and Inspections | CSB | RFP Closed | RFP Closed | 2020-04-29 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
628 | Establishment Licensing and Inspections | CSB | RFP Evaluated | RFP Evaluated | 2020-06-11 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
628 | Establishment Licensing and Inspections | CSB | DG-IP Gate 3 Review/Recommendation | DG-IP Gate 3 Review/Recommendation | 2020-06-30 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
628 | Establishment Licensing and Inspections | CSB | EC-IP Gate 3 Review/Approval | EC-IP Gate 3 Review/Approval | 2020-06-30 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
628 | Establishment Licensing and Inspections | CSB | Contract Awarded | Contract Awarded | 2020-07-20 |  | Delayed within 4 month of projected baseline date. | forecasted completion over 4 months of baseline date
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | TBI | APDC Closure | APDC Closure | 2020-06-20 | 2020-07-28 | Completed within 1 month of projected baseline date. | completed
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | TBI | Pest Control Products C&E Results DB migration to cloud | Pest Control Products C&E Results DB migration to cloud | 2020-03-20 | 2020-08-15 | Completed within 5 month of projected baseline date. | completed
810 | Drug and Health Product Inspections Database | TBI | DHPID rewrite for inspections under AHRA. | DHPID rewrite | 2020-09-30 |  | Forecasted completion date is within 2 month of baseline date | Forecasted completion date is within 2 month of baseline date
A06 | Modernizing the RORB Employee eToolkit | TBI | Virtual Desktop Infrastructure (VDI) for online inspections (Proof of Concept) | VDI (Proof of Concept) | 2018-12-31 | 2020-03-31 | Delays as a result of limited resources in cloud team and competing priorities (mainly release of Canada Food Guide). | completed
A06 | Modernizing the RORB Employee eToolkit | TBI | Virtual Desktop Infrastructure (VDI) for online inspections (Move to Production) | VDI (Move to Production) | 2020-06-30 |  | In queue with cloud team to implement. May be delayed, as cloud team is currently committed to COVID-19 related projects. | forecasted completion over 6 months of baseline date
A06 | Modernizing the RORB Employee eToolkit | TBI | Device procurement (tablet/smartphones/travel docking stations) | Device procurement | 2020-12-31 |  | May complete earlier, if needs arise in Branch. | forecasted completion over 6 months of baseline date
A06 | Modernizing the RORB Employee eToolkit | TBI | SceneDoc Digital Notebook Solution (Testing Phase) | SceneDoc Digital Notebook Solution (Testing Phase) | 2020-03-31 | 2020-03-31 | Results successful. Will propose formal pilot with Cannabis inspection units, to better inform whether to expand to other programs, based uptake by inspectors and other benefits realized. | completed
A06 | Modernizing the RORB Employee eToolkit | TBI | SceneDoc Digital Notebook Solution (Pilot Phase) | SceneDoc Digital Notebook Solution (Pilot Phase) | 2021-03-31 |  | Timeline delayed, as IMSD is prioritizing projects related to Covid-19. This delayed approval process and for necessary IT Security assessment. | forecasted completion over 6 months of baseline date
A06 | Modernizing the RORB Employee eToolkit | TBI | VidCruiter - Virtual Inspection solution | VidCruiter - Pilot with GVP Program | 2021-03-31 |  | forecasted completion date is on schedule | forecasted completion date is on schedule
Kelpie | Kelpie | CPCSD | Procurement for industry partner | Procurement for industry partner | 2020-05-31 |  | Originally planned for RFP (Proservices), however it was later decided to do an RFI through PSPC first, as this may give us must of the info we need for free. | forecasted completion over 6 months of baseline date
Kelpie | Kelpie | CPCSD | Assessment and Feasibility Report | Assessment and Feasibility Report | 2020-10-30 |  | Originally planned for RFP (Proservices), however it was later decided to do an RFI through PSPC first, as this may give us must of the info we need for free. | forecasted completion over 6 months of baseline date
Kelpie | Kelpie | CPCSD | Recommendations Report | Recommendations Report | 2020-11-30 |  | Originally planned for RFP (Proservices), however it was later decided to do an RFI through PSPC first, as this may give us must of the info we need for free. | forecasted completion over 6 months of baseline date
Kelpie | Kelpie | CPCSD | Conceptual Proof of Concept | Conceptual Proof of Concept | 2020-12-31 |  | Originally planned for RFP (Proservices), however it was later decided to do an RFI through PSPC first, as this may give us must of the info we need for free. | forecasted completion over 6 months of baseline date
Kelpie | Kelpie | CPCSD | Request for Information | Request for Information through PSPC | 2020-12-31 |  | Forecasted completion date is within 3 months of baseline date | forecasted completion date is within 3 months of baseline date
809 | PCP IT Modernization | POD-TBI | Gate 2 | Gate 2 | 2020-11-30 | 2021-03-31 | Completion date has been extended due to lack fo support and resources from IMSD. | forecasted completion date is within 6 months of baseline date
811 | CSP IT Modenization | POD-TBI | Gate 2 | Gate 2 | 2021-03-31 |  | Project is currently on schedule but risks being delayed due lack of availability of resources from IMSD | forecasted completion date is on schedule
701 | Appian - Border Mordernization | TBI | Completion of Development | Completion of Development | 2020-01-31 | 2020-05-22 | Forecasted completion date within 3-6 months of baseline date. Schedule extended but development within projected Gate 3 costs. | forecasted completion date within 3-6 months of baseline date
701 | Appian - Border Mordernization | TBI | Gate 4 approval | Gate 4 approval | 2020-03-31 | 2020-10-31 | Gating delayed due to uncertainty and delays to hosting environment from IMSD. | forecasted completion over 6 months of baseline date
701 | Border Mordernization | TBI | Project closeout | Project closeout | 2020-08-30 | 2020-02-19 | Project Closeout adjusted for delays in environment | forecasted completion over 6 months of baseline date
704 | EQMS | TBI | Engage with PSPC on RFP | Engage with PSPC on RFP | 2020-05-31 |  | Delays are expected as engagement due to resource limitations at PSPC | forecasted completion over 6 months of baseline date
704 | EQMS | TBI | Posting of RFP | Posting of RFP | 2020-05-31 |  | Delays are expected as engagement due to resource limitations at PSPC | forecasted completion over 6 months of baseline date
704 | EQMS | TBI | Contract Awarded | Contract Awarded | 2020-05-31 |  | Delays are expected as engagement due to resource limitations at PSPC | forecasted completion over 6 months of baseline date
705 | DAS IT Modernization | Labs | Stakeholder Engagement | Stakeholder Engagement | 2020-05-26 |  | Forecasted completion date is within 6-8 months of baseline date | Forecasted completion date is within 3 months of baseline date
705 | DAS IT Modernization | Labs | Gate 3 Approval | Gate 3 Approval | 2020-09-30 |  | Delays as a result of limited resources and competing priorities at IMSD | forecasted completion over 6 months of baseline date
Cyclops | Cyclops | TBI | Secure Professional Services | Secure Professional Services | 2019-09-30 | 2019-10-16 | Completed | completed
Cyclops | Cyclops | TBI | Development of Prototype | Development of Prototype | 2019-03-31 | 2019-04-16 | Completed | completed
Cyclops | Cyclops | TBI | Testing | Testing | 2020-04-30 | 2020-12-15 | Project delays expected as field testing is not possible due to the Covid situation. | forecasted completion over 6 months of baseline date
Cyclops | Cyclops | TBI | Project closeure | Project closeure | 2020-07-31 | 2021-03-31 | Project delays expected as field testing is not possible due to the Covid situation. | forecasted completion over 6 months of baseline date
Hummingbird | Hummingbird Stream II | TBI & Cannabis | Establish contract with Industry | Establish contract with Industry | 2020-07-31 | 2020-09-18 | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Hummingbird | Hummingbird Stream II | TBI & Cannabis | Procure Satellite Images | Procure Satellite Images | 2020-05-31 | 2020-06-15 | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Hummingbird | Hummingbird Stream II | TBI & Cannabis | Complete Site Analysis for 10 sites | Complete Site Analysis for 10 sites | 2020-10-31 |  | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Hummingbird | Hummingbird Stream II | TBI & Cannabis | Complete Stream II | Complete Stream II | 2020-12-31 |  | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Cipher | Cipher Stream II | TBI & GMP | Hire Data Scientist | Hire Data Scientist | 2020-07-31 | 2020-07-31 | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Cipher | Cipher Stream II | TBI & GMP | Complete Sprint Cycles | Complete Sprint Cycles | 2020-07-31 | 2020-09-01 | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Cipher | Cipher Stream II | TBI & GMP | Complete Test Report | Complete Test Report | 2020-10-01 |  | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date
Cipher | Cipher Stream II | TBI & GMP | Complete Stream II | Complete Stream II | 2020-12-31 |  | Experiencing delays due to COVID | forecasted completion over 6 months of baseline date

## Budget
IP | Project | Directorate | Approved Budget | Forecasted Total Expenditures | Variance / Remaining budget | Expenditure to Date | Project months to date | Burn Rate/month | Months remaining on project | projected spending until project close-out | Variance between remaining approved budget projected spending | Project Authority 2018-19 | Project Expenditures 2018-19 | Project Authority 2019-20 | Project Forecasted Expenditures 2019-20 | Project Authority 2020-21 | Project Forecasted Expenditures 2020-21 | Project Authority 2021-22 | Project Forecasted Expenditures 2021-22 | Project Authority 2022-23 | Project Forecasted Expenditures 2022-23
A03 | Enabling Compliance and Enforcement Program Delivery | POD | 255000 | 255000 | 60000 | 195000 | 24 | 8125 | 12 | 60000 | 0 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 0 | 100000 | 0 | 100000
628 | Establishment Licensing and Inspections | CSB | 9159000 | 8136000 | 1023000 | 1026170 | 37 |  | 28 | 8136000 | 1023000 | 351000 | 233000 | 1159000 | 640170 | 4538000 | 3609000 | 2911000 | 4064000 | 0 | 463000
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | TBI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
810 | Drug and Health Product Inspections Database | TBI | 250000 | 250000 | 173585 | 76415 | 6 | 12736 | 6 | 173585 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 0 | 0 | 0
A06 | Modernizing the RORB Employee eToolkit | TBI | 654000 | 654000 | 614000 | 40000 | 6 | 6667 | 42 | 614000 | 0 | 0 | 0 | 0 | 0 | 347000 | 347000 | 307000 | 307000 | 0 | 0
Kelpie | Kelpie | CPCSD | 157954 | 157954 | 157954 | 0 | 8 | 0 | 6 | 157954 | 0 | 0 | 0 | 0 | 0 | 157954 | 157954 | 0 | 0 | 0 | 0
701 | Appian - Border Modernization | TBI | 2202917 | 1816394 | -386523 | 1496705 | 36 | 41575.1389 | 5 | 319689 | 6141 | 366956 | 366956 | 1516158 | 920989 | 213643 | 613806 | 0 | 0 | 0 | 0
809 | Appian - PCP IT Modernization | TBI | 250000 | 656478 | 406478 | 453707 | 7 | 64815.2857 | 6 | 203000 | - | 0 | 0 | 250000 | 75229 | 581478 | 581478 | 0 | 0 | 0 | 0
811 | Appian - CSP Modernization | TBI | 397409 | 397409 | 0 | 62020 | 3 | 20673.3333 | 6 | 335389 | - | 0 | 0 | - | - | 397409 | 397409 | 0 | 0 | 0 | 0
704 | EQMS | TBI | 1294289 | 1294289 | 0 | 371055 | 25 | 1000 | 14 | 923234 | 0 | 117899 | 117899 | 201530 | 201530 | 619515 | 20000 | 355455 | 970455 | 0 | 0
705 | DAS IT Modernization | Labs | 922000 | 922000 | 0 | 489333 | 18 | 27185.1667 | 11 | 432667 | 0 | 92850 | 92850 | 357150 | 357150 | 472000 | 472000 | 0 | 0 | 0 | 0
Cyclops | Cyclops - Stream 2 | TBI | 341425 | 341425 | 0 | 281068 | 12 | 23422.3333 | 6 | 60356 | 0 | 0 | 0 | 281068 | 281068 | 60356 | 60356 | 0 | 0 | 0 | 0
Hummingbird | Hummingbird Stream II | TBI & Cannabis | 301237.2739 | 301237.2739 | 277994.5839 | 23242.69 | 5 | 4648.538 | 7 | 301237.2739 | 277994.5839 | 0 | 0 | 0 | 0 | 301237.2739 | 301237.2739 | 0 | 0 | 0 | 0
Cipher | Cipher Stream II | TBI & GMP | 295005.9349 | 295005.9349 | 262249.9349 | 32756 | 5 | 6551.2 | 8 | 295005.9349 | 262249.9349 | 0 | 0 | 0 | 0 | 295005.9349 | 295005.9349 | 0 | 0 | 0 | 0

## Budget by Year
IP | Authority vs. Expenditures | Year | Value
A03 | Project Authority | 2018-19 | 85000
A03 | Project Expenditures | 2018-19 | 85000
A03 | Project Authority | 2019-20 | 85000
A03 | Project Expenditures | 2019-20 | 85000
A03 | Project Authority | 2020-21 | 85000
A03 | Project Expenditures | 2020-21 | 25000
628 | Project Authority | 2018-19 | 351000
628 | Project Expenditures | 2018-19 | 233000
628 | Project Authority | 2019-20 | 1159000
628 | Project Expenditures | 2019-20 | 640170
628 | Project Authority | 2020-21 | 4538000
628 | Project Expenditures | 2020-21 | 0
628 | Project Authority | 2021-22 | 2911000
628 | Project Expenditures | 2021-22 | 0
A04 | Project Authority | 2020-21 | 0
A04 | Project Expenditures | 2020-21 | 0
810 | Project Authority | 2020-21 | 250000
810 | Project Expenditures | 2020-21 | 250000
A06 | Project Authority | 2020-21 | 347000
A06 | Project Expenditures | 2020-21 | 347000
A06 | Project Authority | 2021-22 | 307000
A06 | Project Expenditures | 2021-22 | 307000
Kelpie | Project Authority | 2021-22 | 157955
Kelpie | Project Expenditures | 2021-22 | 157955
IP000 | Project Authority | 2019-20 | 75000
IP000 | Project Expenditures | 2019-20 | 75000
IP000 | Project Authority | 2020-21 | 250000
IP000 | Project Expenditures | 2020-21 | 250000
704 | Project Authority | 2018-19 | 117899
704 | Project Expenditures | 2018-19 | 117899
704 | Project Authority | 2019-20 | 201530
704 | Project Expenditures | 2019-20 | 201530
704 | Project Authority | 2020-21 | 619515
704 | Project Expenditures | 2020-21 | 20000
704 | Project Authority | 2021-22 | 355345
704 | Project Expenditures | 2021-22 | 970455
705 | Project Authority | 2018-19 | 92850
705 | Project Expenditures | 2018-19 | 92850
705 | Project Authority | 2019-20 | 357150
705 | Project Expenditures | 2019-20 | 357150
705 | Project Authority | 2020-21 | 472000
705 | Project Expenditures | 2020-21 | 47651
701 | Project Authority | 2017-18 | 106160
701 | Project Expenditures | 2017-18 | 106160
701 | Project Authority | 2018-19 | 366956
701 | Project Expenditures | 2018-19 | 366956
701 | Project Authority | 2019-20 | 1516158
701 | Project Expenditures | 2019-20 | 983390
701 | Project Authority | 2020-21 | 213643
701 | Project Expenditures | 2020-21 | 390529
Hummingbird | Project Authority | 2020-21 | 301237.2739
Hummingbird | Project Expenditures | 2020-21 | 301237.2739
Cipher | Project Authority | 2020-21 | 295005.9349
Cipher | Project Expenditures | 2020-21 | 295005.9349

## Status
IP | Project | Current Stage | Directorate | Project Objectives | Current Project Status | Overall Project Health | status | stage
A03 | Enabling Compliance and Enforcement Program Delivery | 4 | TBI | To address constraints identified in Comprehensive Review from 2018, related to business streamlining. Project goal is to provide off-the-shelf software solutions in two subprojects under the Enabling Compliance and Enforcement umbrella: 1. Learning Management System (LMS) 2. Jira (Inspection Scheduling System (ISS), Client Services) | LMS: Edubrite was selected as the software platform of choice for its competitive pricing and ability to meet the vast majority of ROEB’s requirements Initially piloted with Cannabis Directorate, LMS has been scaled up to other program areas of ROEB, including: TVCEP, HPIL, CS, HP Labs; elimination of manual tracking and reporting on inspector training for those program areas. Created a user base of over 250 users in ROEB, and licensing agreements through 2021 for up to 750 Jira: Implemented a Jira instance to track the scheduling of Cannabis inspections Acquired add-on licenses for Jira to integrate with Outlook Created a user base of more than 100 employees and licensing through 2021 for up to 250 | Green | On-Track | 4
628 | Establishment Licensing and Inspections | 3 | CSB | The project seeks to put in place an enterprise-wide solution, Establishment Licencing & Inspection System (ELIS), which will support all Health Canada programs that provide authorizations to conduct regulated activities with regulated products. | Overall Comments Status: Overall project health is yellow due to the timeline delays with proceeding with the RFP. We are working with PSPC to ensure RFP can be posted ASAP. Currently, the RFP is with PSPC for final approval before posting. ● DG Steering Committee has taken the decision to outsource the configuration/integration of the solution via an SBIPS RFP in Nov 2018 ● Endorsement from TBS concept case received ● Gate 2 visit to DG-IP took place on December 18th DG-IP, with recommendation going to the January 16, 2019 EC-FIPT meeting. ● EC-FIPT approval received on January 16, 2019 to proceed with Stage 3 activities. Recommendation to conduct LEAN analysis for Medical Device Program (MD), costing to be covered by DM reserve ● PIA work completed (no PIA required for any programs); project plan and costing will be adjusted to reflect the change. ● Preliminary TRA will not be conducted until after Gate 3 since the project will be outsourced via RFP. ● Technical resources were deviated away from deliverables to conduct the fit Gap analysis of the CTLS system as requested by DG-SC in May. The results of this analysis were that IP-628 continue as planned. ● Information and Technology architectures work was delayed by a month, but now completed. ● Draft SoW finalized for internal, and subsequent signature of Section 32 for RFP and engagement of PSPC. ● Form 9200 for requisition submitted to PSPC for formal engagement, with draft Evaluation criteria for discussion with PSPC have also been completed. ● PSPC has now been engaged, and they have provided an 8 month estimate to the point of having vendor awarded. Project is paying for dedicated PSPC resource to accelerate schedule. ● Significant rework of SOW has been needed as per feedback from PSPC but this work is completed. | Yellow | On-Track | 3
A04 | ROEB Aging IT (Stabilization/Modernization/Transformation) | Execution | TBI | There are 28 RORB IT solutions that are considered Aging IT. Systems will be addressed by priority and grouped with projects of similar priority. There are 28 RORB IT solutions that are considered aging IT. RORB will conduct a review of aging IT systems and produce a plan to remediate through tolerating, migrating, innovating, or eliminating these systems. High priority systems under aging IT include: Inspection Reporting System, Incident System, Export Certificate Database, and the Laboratory Information Management System. | • ROEB IT Roadmap created with IMSD, detailing 3 year plan. • Leverage app analysis report and addressing high risk applications - Initial focus on highest risk applications. | Green | On-Track | Execution
810 | Drug and Health Product Inspections Database | Execution | TBI | As part of the regulatory transparency priority, seven different programs make use of the online Inspection Database to post their inspection reports to the Healthy Canadians website, where the public has access to them. There are requirements to update this database and improve the functionality of the website as well as expand the amount of information available. | • MDAP enhancements completed. • Migration of Pesticide Registrant Inspection database from HRE to cloud completed. • Due to the challenges experienced when making changes to DHPID in its current form, no further enhancements will be made until DHPID system is rewritten. • DHPID rewrite: Development work underway to initially accomodate posting of new inspections under AHRA, now anticipated to begin sometime in winter 2021. After this, existing DHPID databases will be migrated into new system, and/or new programs can be on-boarded. | Green | On-Track | Execution
A06 | Modernizing the RORB Employee eToolkit | Execution | TBI | This project focuses on providing off-the-shelf hardware and software solutions to employees working in the RORB program to modernize the workforce and enable a seamless transition from office to the field. It addresses challenges in the technology currently made available to RORB employees and proposes alternative solutions that would allow them to do their jobs more efficiently. | • Mobile Tech: To date, at least 710 tablets, 762 smartphones have been deployed to ROEB (including devices deployed through etoolkit project and those procured by program themselves). • Virtual Workstations: 3 pilot workstations tested by inspectors (HPC, TVC, Pesticides). Next phase is to move Proof of Concept model into production, starting with HPC and 10 concurrent licenses, and then adding programs in sequence. • Epost Connect: Contract renewed Feb 25th for one more year. Still working under IAO while Canada Post completes necessary security assessment, which is now underway with TBS. Programs using epost include: Cannabis, Controlled Substances, GVP, HPCRM, HPIL, MDIU, BPC. Due to increase in accounts since Covid, upgraded subscription commitment level to 'gold'. Also, looking exploring alternative to epost Connect (Liquid Files), which looks to be cheaper and may address some of the annoyances users have with epost - mainly, it works more like a drop box (secure link) instead of stakeholder needing to register, and also provides ability to download multiple files at once. • Completed testing of digital notebook solution (SceneDoc), using dummy data, with inspectors from Cannabis, HPC(CV), and CPS, which would enable inspectors to efficiently capture digital content (notes, pictures), and also to digitize forms used, in the field. As testing was successful, next phase is to implement formal pilot with Cannabis and HPC, using real data, which will allow us to better assess whether to expand to other ROEB programs, based on overall uptake by inspectors and other benefits realized. • As a result of COVID-19, inspectors need better solution for conducting certain inspection activities remotely. VidCruiter will be piloted for this purpose with GVP program, between September 30, 2020 - March 31, 2021. | Green | On-Track | Execution
Kelpie | Kelpie | Planning | TBI/CPCSD | To explore whether it’s possible to use artificial intelligence to monitor social media and identify “posts” promoting vaping products that could be appealing to youth. | Note: The original plan for this SF project was for RFP through Proservices, to partner with a consultant to assist us in better understanding the possibilities of using AI to monitor social media posts promoting vaping products that could be apealing to youth. However, after starting this process with MAMD and discussing with PSPC's AI solutions team, it was decided that it's a better option for us to first do a RFI (Request for information) through PSPC, as this will enable us to pose questions directly to vendors in PSPC's AI Source list, which will help us to better understand the market and acquire a solution to meet our requirements. (Basically, this should give us the info we need for free) • We were delayed by a few months due to the procurement review process taking longer than anticipated. | Yellow | Caution | Execution
704 | EQMS | 3 | TBI | Replace the lagacy QSI solution with a new Quality Management Solution to meet the requirements of ISO 9001:2000 | POD-TBI received Gate 2 approval at EC-FIPT on June 27, 2019. POD-TBI is currently working with MAMD to engage PSPC to post the RFP. PSPC received the request on December 2, 2019, however the file has yet to be assigned to an Officer at PSPC. MAMD has advised ROEB TBI that posting of the RFP could take 9-12 months, which is a significant risk to project timelines. PSPC informed TBI in September 2020 that the file is on hold due to resourcing constraints as a result of COVID-19. | Yellow | Caution | 3
705 | DAS IT Modernization | 3 | Labs | Introduce an electronic portal for DAS and its clients to digitally enable exhibit submission, issuance of the Certificate of Analyst and improve communication. The project will also introduce the Electronic Lab Notebook, which is the first step in the DAS transition to a paperless lab. | The project received Gate 2 approval in September 2019 and the project is currently in Stage 3. . While the project is behind the original schedule, it is anticipated that some time can be recovered in subsequent stages. The program has decided to conduct stakeholder engagement activities with its law enforcement clients to inform them of the project and seek input on the overall direction. The initial sessions will be held in May 2020. Competing priorities at IMSD and resourcing challenges as a result of COVID-19 have impacted the proejct timeline. Technical options for the portal are still being reviewed as an SSC proejct has impacted the ability to proceed with the initial tehcnical plan. These project issues have delayed Gate 3 from April to December 2020 (TBC). | Red | Caution | 3
701 | Border IM/IT Modernization | 4 | TBI | Invest in a modern IM/IT system for the Health Products Border Program to bring their data collection and management processes onto a single mobile platform. | The project has completed UAT and is in the final stages of development as it awaits the delivery of the Protected B Cloud environment. | Yellow | Delayed | 4
809 | PCP IT Modernization | 2 | POD-TBI | IM/IT system that will modernize the Pesticide Compliance Program (PCP) to support their regulatory compliance and enforcement activities across Canada and provide them with the tools they need to deliver on their mandate. | Development work and sprints have been completed. Project has been delayed as IMSD does not have sufficient resources to support the infrastructure and deployment of the product. | Red | Delayed | 2
811 | CSP Modernization | 2 | POD-TBI | This project aims to proceed with the development of a new IT system that provides modernized & interconnected tools for the Controlled Substance Program(CSP) in support of the delivery of its mandate of controlled substances regulatory compliance and enforcement oversight across Canada. | Project on schedule and currently undergoing 6 month projected development schedule. | Green | On-Track | 2
Cyclops | Cyclops | 2 | TBI | The project is proposing to create a new process enabled by a digital-tool (smartphone camera / wearable device) to virtualize optically represented text on the label, query the data via existing databases, identify and highlight instances of non-compliances, and visually depict the issue by overlaying the information back on to the camera/device feed. | The project has successfully completed prototype development and is ready for field testing. Because of Covid, testing will be however delayed till Inspectors are allowed to go back into the field and test the prototype. | Yellow | Delayed | 2
Hummingbird | Hummingbird Stream II | Planning | POD | Test satellite imagery technology to aid Cannabis outdoor inspections | The experiment will pivot and only focus on sattellite imagery to test potential support of cannabis inspections. Due to COVID, the testing phase will include 12-15 sites, where images will be collected monthly from June to October. This pivot will be presented to Solutions Fund at the next quarterly report. This risk has been identified since June -- it has now become an issue. Examining sample satellite imagery to understand techniques and approaches to develop best fit protocols; | Yellow | Delayed | Testing
Cipher | Cipher Stream II | Planning | POD | Test Machine Learning (Artificial Intelligence) technology to automatically risk rate inspection observations | The focus of Cipher Stream 2 is on the development, building and testing of a Minimum Viable Product (MVP). The project was approved in December 2019. Since January 2020 the project team has been focussed on project planning and project promotion across ROEB. Accomplishments: • Finalized Workplan and Obtained Approvals • Developed and presented a Project Cipher proposal to the Canadian School of Public Service (CSPS) • Project Cipher was highlighted/presented at a recent ADM Town Hall where the theme was compliance and enforcement transformation. • Identified project team members. • Identified inspection data sources required to build and validate the MVP. Exported approximately 27,000 inspection observations from the Inspection Reporting System to assist with MVP development. • Established a partnership with CSPS - and connecting with other departments like ECCC and TC to share results of Cipher • Initiated the building of the Minimum Viable Product o Web application developed in flask (Python micro-framework) that predicts the risk associated to an inspector’s comment. o Machine learning algorithm that also predicts the type of regulation associated to an inspector’s comment. | Yellow | Delayed | Testing

## Project Risk
IP | Project Name | Risk | Risk description | Probability | Impact | Mitigation Strategy | Risk Management Lead
A03 | Enabling Compliance and Enforcement Program Delivery | Technical | Engagement of IMSD/SSC in project activities. Ensure appointment of technically qualified team. | Green | Yellow | Ensure communication is frequent and objectives are clear between the associated technical groups. | TBI
A03 | Enabling Compliance and Enforcement Program Delivery | Resourcing | Engagement with programs to ensure availability of SMEs as required for each sub-project. | Green | Green | At subproject outset and during its ongoing maintenance and support, ensure that the project authority is available to make timely decisions | TBI
A03 | Enabling Compliance and Enforcement Program Delivery | Uncertainty | Ensure linkages and awareness of larger investment plans across the Branch to be able to shift priorities accordingly. | Green | Yellow | Coordinate with National Learning Unit. Establish regular meetings and project updates. | TBI
A03 | Enabling Compliance and Enforcement Program Delivery | Technical | Jira Hosting: Coordination with IMSD to resolve hosting environments for test, dev, prod. | Yellow | Red | Ensure communication is frequent and objectives are clear between the associated technical groups. | TBI
A03 | Enabling Compliance and Enforcement Program Delivery | Resourcing | Availability of TBI resources: Many overlapping projects make it difficult to have a reliable schedule and delivery of service to clients | Green | Yellow | An overall Enabling C&E plan for the branch has been developed. Continue to update project schedules as new subprojects are launched and as activities are completed. | TBI
A03 | Enabling Compliance and Enforcement Program Delivery | Compliance | Bill C-81 has implications on WCAG requirements for employee learning. Will require overhaul of all uploaded content that is not WCAG compliant, or a waiver to accept the risk of non-compliance in a limited capacity | Yellow | Red | Develop an implementation plan by Q4 2020 in advance of the Act coming in to force. | TBI
628 | Establishment Licensing and Inspections | IT Capacity | There are a large number of projects in HC/PHAC competing for internal and contracted IT skillsets that this project will require. | Green | Red | Project will outsource the configuration and integration of the solution via an SBIPS RFP, and award contract to bidder that can ensure required skillsets and resources are provided. | CSB/BREAD/Chad MacKinnon
628 | Establishment Licensing and Inspections | Procurement Uncertainty | Uncertainty on full project costs and timelines due to SBIPS RFP approach to solution development. | Red | Yellow | Project is working with PSPC and MAMD. Project will learn from past SBIPS RFPs, including what was done by CFIA for their ESDP solution. Project is paying for PSPC FTE to work on the procurement. | CSB/BREAD/Chad MacKinnon
628 | Establishment Licensing and Inspections | Project Resources | All program resources are part-time on the project. This could constrain the ability to conduct required project activities in a timely manner. | Green | Red | Project will continue to provide clear project expectations of the Program resources and obtain full commitment from Program senior managements. Assign dedicated Business Analyst resource to support SMEs. | CSB/BREAD/Chad MacKinnon
628 | Establishment Licensing and Inspections | External Solution Partners | Components of the overall ELIS business solution are the responsibility of partners and are not all fully developed or implemented. Examples are GCDocs, and HC Gateway. | Yellow | Red | Project will develop Service Level Agreements (SLA) with each of the partners; develop integrated project schedules and frequent monitoring of their deliverables. | CSB/BREAD/Chad MacKinnon
628 | Establishment Licensing and Inspections | Business Transformation | Current business processes may not align with ELIS system design. | Yellow | Yellow | Project has developed a business transformation plans so that effort and change requirements will be clear for program business process and change management activities in stage 4 execution. LEAN analysis has also been undertaken and results shared with Director level governance committee. | CSB/BREAD/Chad MacKinnon
628 | Establishment Licensing and Inspections | SSC Capacity | Project timelines will be impacted by SSC intake processes which may introduce project delays pending SSC availability. | Yellow | Yellow | Project engaged with SSC early in stage 3 and provided funding to ensure their involvement ands capacity. This will need to be done again in stage 4 to ensure any SSC risks are addressed early Project will also maintain project as very high on SSC projects list (#17 in GoC project list, #2 in HC project list as of February 2019) | CSB/BREAD/Chad MacKinnon
628 | Establishment Licensing and Inspections | Funding | As a multi-year project, there is risk that required funds for the project will not be available in futures years. | Green | Red | Project governance will be leveraged to ensure funding is supported. Project is #17 on the GoC list of projects; #2 in HC project list. If funding is not available, options to de-scope or delay would be considered. | CSB/BREAD/Chad MacKinnon
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | Schedule | Competing priorities witin IMSD, SSC, and business groups could delay work. | Green | Green | Typically find ourselves in a reaction position to requests from IMSD and SSC, whereby they are given a priority and we are expected to comply. | IMSD
810 | Drug and Health Product Inspections Database | Resourcing | Due to Covid-19, IMSD priorities may delay their ability to push changes to DHPID to CATE and production. | Yellow | Yellow | Scheduling development work early, which should give ample time for UAT and push to production. | TBI
A06 | Modernizing the RORB Employee eToolkit | Resourcing | SceneDoc Pilot risks being delayed from planned timelines, due to IMSD prioritizing Covid related projects. | Yellow | Yellow | Working with IMSD to work project to necessary channels asap (TAC, BIC, procurement) | TBI
A06 | Modernizing the RORB Employee eToolkit | Resourcing | Moving virtual workstations (VDI) to production at risk of being delayed, as cloud services team dedicated to Covid projects. | Yellow | Yellow | Worked with IMSD to get project in queue with cloud services asap. | TBI
Kelpie | Kelpie | Technical | Current technology may not be able to identify ads promoting vaping products that could be appealing to youth. | Yellow | Yellow | Even if this is the case, this project will still enable us to better understand what is possible and the extent to which technology can assist with monitoring online ads. | TBI
Kelpie | Kelpie | Functionality | Legal may advise that program should not collaborate with social media companies, since they are considered a regulated party under the Act. | Yellow | Yellow | It may not be necessary to collaborate directly with social media companies, if data is otherwise accessible. In any case, legal will be engaged. | TBI
Kelpie | Kelpie | Resourcing | Insufficient resources available from business. Since there is limited staff within the program. | Yellow | Red | Coordinate closely with the program in order to use any resources provided as efficiently as possible. | TBI
Kelpie | Kelpie | Resourcing | There may be costs associated with accessing online data. | Yellow | Yellow | If so, this will be considered when assessing the possible solutions. | TBI
Kelpie | Kelpie | Functionality | There may legal and/or privacy issues with accessing data. | Yellow | Yellow | Legal will be consulted. This will be considered when assessing the possible solutions. | TBI
704 | EQMS | Funding | Current costing for a COTS solution is based upon limited, “generic”, samples from three vendors. | Green | Yellow | Revise costing when assessing the RFP | TBI
704 | EQMS | Resourcing | Inability to help with transition, configuration of QMS system to other programs (if successful) due to resource capacity within ROEB-TBI, IMSD and implicated programs. | Green | Yellow | Work closely with programs when scheduling onboarding to ensure availability | TBI
704 | EQMS | Technical | Proposed architecture is new to HC as an enterprise SaaS and how it will be leveraged as an enterprise standard. Many technical and security issues are still unknown. | Green | Yellow | Work with IMSD to assess viability of hosting solutions | TBI
705 | DAS IT Modernization | Schedule | Competing departmental priorities may impact timelines for procurement and implementation of new LabWare components | Green | Yellow | Work closely with programs when scheduling project activities to ensure availability | TBI
705 | DAS IT Modernization | Resourcing | COVID travel restrictions will impact the ability to deliver the ELN Pilot as planned; alternative delivery methods will need to be evaluted. | Yellow | Yellow | Consult with LabWare, IMSD, and DAS resources to plan for alternative delivery. Postpone pilot from Stage 3 to Stage 4. | TBI
705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI | 705 | DAS IT Modernization | Technical | A major firewall project at SSC may impact the projects ability to proceed with the initial technical solution for the portal component. SSC, IMSD, and project resources are working jointly to assess the issue and propose a way forward. | Yellow | Red | Consult with LabWare, IMSD, and DAS resources to plan for alternative technical solution. | TBI
701 | Border Modernization | Complex product installation/configuration | Proposed architecture is new to HC as an enterprise SaaS and how it will be leveraged as an enterprise standard. Many technical and security issues are still unknown. | Red | Yellow | Project entering Stage 4 in conjunction with IP603 to harness synergies and build quickly on lessons learnt. Technical resource from IMSD to participate in the development process, and Vulnerability Assessment Scans to be conducted regularly. | TBI
701 | Border Modernization | Potential for non-compliant applications | BPMs enable application development without the oversight of departmental IM/IT. This can lead to HC applications that do not comply to HC and GoC technology standards. | Red | Yellow | Technical Expert from IMSD to participate in the development of the solution to provide methodology standards, alignment w/ HC and GoC IM/IT initiatives, best practices for development and deployment. This will ensure that any significant changes to the platform are reviewed by IMSD. | TBI
809 | PCP IT Modernization | Hosting Environment | Delay of timelines for the project to get onto HC test environment if IP701/603 are not on there yet. Documentation required by IMSD such as VA & TRA scans are contingent on a hosting environment, and these cannot be done if PCP is being held idle, preveting from the database built by Vuram to go live. | Red | Yellow | We will be on contractors testing environment in the meanwhile until IMSD gets sorted out | IMSD
811 | CSP IT Modernization | Hosting Environment | Delay of timelines for the project to get onto HC test environment if IP701/603 are not on there yet. Documentation required by IMSD such as VA & TRA scans are contingent on a hosting environment, and these cannot be done if PCP is being held idle, preveting from the database built by Vuram to go live. | Yellow | Yellow | We will be on an Appian Demo environment until IMSD gets sorted out. | IMSD
701 | Border Modernization | Protected B Cloud may be delayed | Protected B cloud is expected to be available in FY19/20 Q3. Delays in availability past Q3 or restrictions in functionality in early releases (eg. Cloud to Ground Pipeline) may impact production timeline. | Yellow | Green | Protected B Cloud availability will be monitored through Q2 2019/20. Implementation date is scheduled for Q3 2019/20 and allows for flexibility. TBI will work with HPFB (IP603) to start procurement process to deploy SSC On-Prem in the event protected B Cloud is not ready by deployment date. | TBI
Cyclops | Cyclops | Technology readiness | Technology required for solution may not be appropriate or ready in the current environment | Green | Yellow | While a majority of the requests for the prototype have been configured, the testing might provide additional requirements that need to be addressed. | TBI
Cyclops | Cyclops | HC infrastructure | Current HC infrastructure may not support the interfacing required for the solution(s) available. | Green | Yellow | IMSD has confirmed compatiblity to existing environment. There are however some technical issues still to be resolved before the risk can be considered mitigated. | TBI
Hummingbird | Hummingbird Stream II | COVID-19 | Prolonged impact of COVID-19 to Cannabis Directorate operations, which directly impacts Hummingbird; | Red | Red | Request extension to Solutions Fund for next growing season | POD
Cipher | Cipher Stream II | COVID-19 | Team member availability – Covid-19 work priorities | Yellow | Red | Extend timelines with Solutions Fund | POD/GMP
Cipher | Cipher Stream II | Data | Ensuring data used in training and testing is consistent and trustworthy. | Yellow | yellow | Leverage eCES to ensure quality of data | POD/GMP
Cipher | Cipher Stream II | Language | Use of multiple languages (French and English) can introduce complexity - different words are used to capture the same meaning. | Green | yellow | Use English only for MVP | POD/GMP
Cipher | Cipher Stream II | MRA | The impact of Cipher on Mutual Recognition Agreements. | Green | yellow | Stakeholder outreach to share and learn together with other jurisdictions | POD/GMP
Cipher | Cipher Stream II | Communication | Negative perception of Cipher by inspectors. | Yellow | yellow | Stakeholder outreach and continuous engagement / co-development with inspectors | POD/GMP
Cipher | Cipher Stream II | Data | Data formatting and availability for foreign site evidence review testing. | Yellow | yellow | Reliance on technology that is able to reconcile scanned PDF technology | POD/GMP

## Project Issues
IP | Project Name | Issue | Issue Description | Impact | Target Date for Resolution | Resolution Strategy | Resolution Lead
A03 | Enabling Compliance and Enforcement | Resourcing | Inconsistent availability of resources in the program areas to work on the projects is resulting in delays and re-adjustment of objective start/finish dates. | Green | 2020-09-01 | At subproject outset and during its ongoing maintenance and support, ensure that the project authority is available to make timely decisions | TBI
A03 | Enabling Compliance and Enforcement | Resourcing | Some program representatives seem to not have the authority to make determinations on behalf of their group (eg course/program composition), requiring senior management engagement for trivial decisions. | Green | 2020-12-31 | Ensure that program area SMEs are imbued with authority to make decisions about the composition of LMS materials. | TBI
A03 | Enabling Compliance and Enforcement | Technical | Dev server faced an unforeseen shutdown early Jan 2020, prompting an urgent process to start migration to GC Cloud. Old dev server is being help up for time being but will need to be vacated as soon as possible." | Yellow | 2020-05-31 | Coordinate with DevOps and CEG to transfer existing Jira instance to GC Cloud. | TBI
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | None
810 | Drug and Health Product Inspections Database | Technical | Current configuration (inefficient coding, outdated) makes any enhancements very resource intensive for both IMSD and SME. | Yellow | 2020-12-31 | DHPID system being rewritten, initially to implement new DB for inspections under AHRA, following which current DBs will be migrated to new system. This will also better enable us to on-board new programs, and be ready for when data will come from IP-628. | TBI
A06 | Modernizing the RORB Employee eToolkit | Resourcing | SceneDoc Pilot delayed by approximately 6 months, due to IMSD prioritizing COVID-19 related projects. Currently, the delay is due to IT Security backlog, resulting in them not being available to complete necessary TRA and SAAR. | Yellow | 2020-11-15 | While waiting for IT Security resources, was able to obtain some additional informaiton and checklist for the vendor to gather the information that will be necessary for the assessment. Have provided this info to IT Security in case they're able to work on the side. | TBI
Kelpie | Kelpie | Schedule | RFP through Proservices did not result in any vendors with the AI expertise we had hoped for. It seems that ProServices is not yet geared towards AI work. After starting this process with MAMD and discussing with PSPC's AI solutions team, it was decided that it's a better option for us to first do a RFI (Request for information) through PSPC. | Green | 2020-10-01 | RFI (Request for information) submitted for posting through PSPC. This will enable us to pose questions directly to vendors in the AI Source list, which will help us to better understand the market and acquire a solution to meet our requirements. | TBI
704 | EQMS | Schedule | Delays in posting the RFP with PSPC. PSPC does not have the capacity to work on the RFP and it has been put on hold. | Red | 2020-12-31 | Continue to push for PSPC attention via MAMD | TBI
701 | Border IM/IT Modernization | Hosting Environment | I1. Delays and issues in delivery of Protected B Cloud from IMSD. | Yellow | 2020-07-15 | The database is currently deployed on the AWS Staging and awaiting deployment on Production. | IMSD
701 | Border IM/IT Modernization | VA Scans & TRA | I3. VA and TRA testing cannot proceed until the database is in its final hosting environment. | Yellow | 2020-07-15 | Resources have been aligned to complete the deliverables as soon as the lift and shift to the Protected B Cloud has been completed. | IMSD
809 | PCP IT Modernization | Schedule | IMSD has delayed any discussions on costing and scheduling in order to support the environment, until DG-IP in October that would allow to identify a path forward. | Red | 2020-10-31 | Awaiting DG-IP presentation in October, to be led by BREAD. Will support and provide input for onboarding all the Appian projects. | IMSD
Cyclops | Cyclops | Field testing | Field testing of the prototype cannot be completed until the restrictions from Covid have been lifted. | Yellow | 2020-09-01 | Alternative testing strategies have been developed, and will be implemented if field testing is not feasible in the near future. | TBI
Hummingbird | Hummingbird Stream II | Schedule | · Establishing Industry partner / contract for drone and satellite data technology support. Has been delayed to May 2020; | Red | 2020-07-31 | Onboarding industry partner will be delayed and project schedule will need to be adjusted. Pivot is being planned | TBI
Hummingbird | Hummingbird Stream II | Schedule | · Executing on-site experiment using drones due to COVID-19 policies; | Red | 2020-12-01 | Wait until next growing season | TBI
Hummingbird | Hummingbird Stream II | Schedule | · Inability to collect any RBG or NIR data via Drones to conduct any inspection analysis; and | Red | 2020-12-01 | Wait until next growing season | TBI
Hummingbird | Hummingbird Stream II | Schedule | · Inspections severely impacted; only high-priority/high-risk inspections are being conducted. | Red | 2020-12-01 | Wait until next growing season | TBI
Cipher | Cipher Stream II | Schedule | March 2020 Face-to-Face Sprint Planning meeting - cancelled due to Covid-19 travel restrictions. | Yellow | 2020-07-31 | Have meeting in July when new Data Scientist is expected to start | TBI
Cipher | Cipher Stream II | Schedule | Data Scientist hiring – a data scientist was identified but there were delays during the hiring process. | Yellow | 2020-07-31 | Have meeting in July when new Data Scientist is expected to start | TBI

## Capital
IP | Capital | Year
628 | 0 | 2020-21
628 | 450000 | 2021-22
705 | 150000 | 2020-21